## Agile Project Plan - BLANK
CHECKCARE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Website
| Checkcare | Lailatul Maghfiro | 2021-10-06 | 2021-11-25 |  | 25% |  | SCOPE STATEMENT | Aplikasi yang dapat membantu pengguna untuk menentukan pelayanan kecantikan yang ingin dipilih.
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 | Homepage Website | Lailatul Maghfiro |  | 2021-10-06 | 2021-11-06 | 1 | In Progress
| Dashboard |  | Jihan, Febri |  |  |  | 12 | In Progress
| Login/Registrasi |  | Febrian Tri H. |  |  |  | 7 | In Progress
| Profil Checkcare |  | Febrian Tri H. |  |  |  | 5 | In Progress
| Sprint 2 | Konten Website | [5 empty] | Not Started
| CRUD Detail Harga | [6 empty] | Not Started
| Profil/Akun User | [6 empty] | Not Started
| Pengaturan | [6 empty] | Not Started
| Sprint 3 | [6 empty] | Not Started
Status & Detail Pesanan
User Payment
Testing

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.